## Overview
RECON — V1 MVP Brief (Claude Code Ready)
Project | RECON — Route Environment & Condition Observation for Navigation
Domain | recon.mettlecycling.com
Primary user journey | User pastes a route link (Strava, MapMyRide/MapMyFitness) or uploads a route file (GPX/TCX/FIT). RECON normalizes the route geometry + elevation, segments it, enriches it from data sources, and returns: (1) a route dossier, (2) an interactive map with overlays, (3) a plain-language ride planning summary.
V1 goal | Deliver a high-signal route dossier + map overlays using sources we can access reliably without partner deals, and design the architecture so richer sources can be swapped in for V2.
Non-goals for V1 (explicit) | • Universal parcel-accurate private property lines • Guaranteed business hours freshness everywhere • Universal municipal closure coverage • Social photo harvesting from third-party sites without explicit supported APIs / permissions
Key MVP outputs | • Surface breakdown (best-effort) • Public lands / land manager overlay (US-focused) • Weather-by-segment (US: NWS; Global fallback: Open-Meteo in dev) • Water + resupply + bike shop + emergency POIs • Supply gaps (distance between critical points) • Trail conditions (optional: Trailforks if approved) • Visual recon imagery (optional: Mapillary; V2: prefer Strava imagery where supported)

## MCP_Servers
Server | Responsibilities | Inputs | Outputs
Route Intake Server | Parse GPX/TCX/FIT; optional Strava/MapMyFitness import; normalize route; segment & sample points | File upload, OAuth tokens, route URL | Canonical route JSON + sampled points
OSM/Overpass Enrichment Server | Surface/access tags; POIs (water, stores, shops, shelters); compute gaps | Route geometry + buffer distance | POI list + surface stats + access flags
Weather Enrichment Server | Forecast/alerts along route; segment summaries; risk flags | Sampled points + time window (optional) | Weather-by-segment + alerts
Public Lands Server | Overlay PAD-US / Federal lands; state trust land adapters where available | Route geometry + buffer | Land manager polygons + segment intersections
Coverage Server (US-first) | Cell coverage confidence overlay (US); degrade gracefully elsewhere | Route geometry + buffer | Coverage confidence per segment
Conditions/Closures Server | Trailforks (if approved) + region connectors later | Route geometry + area | Dated condition reports + closure notes
Visual Recon Server (optional in V1) | Route-adjacent imagery points using Mapillary | Route geometry + sampling strategy | Representative images/links near route
Auth & Athlete Context Server (V2) | Strava athlete context, notes, richer imagery where supported | OAuth tokens | Rider-specific notes and personalization

## Epics_Stories
Epic ID | Epic | Story ID | User Story | Acceptance Criteria | Dependencies | Release
E1 | Route Intake | S1.1 | Upload GPX/TCX/FIT and get a normalized route object. | Uploads parse; route polyline + distance + elevation gain computed; errors are actionable. | FIT SDK; GPX/TCX parsers | V1
E1 | Route Intake | S1.2 | Connect Strava and import one of my routes. | OAuth works; list routes; select one; pull route geometry; store per-user token securely. | Strava API | V1
E1 | Route Intake | S1.3 | Connect MapMyFitness and import a route. | OAuth works; fetch route geometry; normalize. | MapMyFitness API | V1 (optional)
E2 | OSM Enrichment | S2.1 | See surface breakdown for my route. | Compute % by surface/highway classes with confidence notes. | Overpass API | V1
E2 | OSM Enrichment | S2.2 | See water/resupply/shops along the route. | POIs returned within corridor; dedup; categorize; compute distances. | Overpass API | V1
E2 | OSM Enrichment | S2.3 | See emergency bailout options. | Identify towns/transit/bike shops/shelters; provide nearest points. | Overpass API + heuristics | V1
E3 | Weather | S3.1 | See weather by route segment. | Sample points; call weather API; summarize by segment; flag risk. | NWS (US) / Open-Meteo fallback | V1
E3 | Weather | S3.2 | See active alerts affecting my route. | Pull alerts; attach to segments; show severity and timing. | NWS Alerts API | V1 (US)
E4 | Public Lands | S4.1 | See if my route crosses NPS/USFS/BLM/etc. | Intersect route corridor with PAD-US / Federal Lands; display land manager. | PAD-US / Esri federal lands | V1 (US)
E5 | Coverage | S5.1 | See cell-coverage confidence along the route (US). | Intersect corridor with FCC coverage layer; produce confidence bands. | FCC National Broadband Map datasets | V1 (US)
E6 | Conditions | S6.1 | See recent trail reports near the route, with dates. | If Trailforks approved, pull reports; show date + source; else hide feature. | Trailforks (approved) | V1 optional / V2
E7 | Visual Recon | S7.1 | See representative on-route photos for context. | Use Mapillary to fetch nearby imagery; select a small set; show source links. | Mapillary API | V1 optional
E7 | Visual Recon | S7.2 | See Strava-sourced route imagery where supported. | Prefer Strava images/metadata for routes/segments if available via supported API scopes; fallback Mapillary. | Strava (future) | V2

## Data_Sources
Feature / Functionality | Primary Source | Primary URL | Access Model | Coverage | Freshness | V1 Use | V2 Upgrade / Note | Secondary Options (URL) | Notes / Limitations
Route import (Strava) | Strava API v3 (Routes endpoints) | https://developers.strava.com/docs/reference/ | OAuth 2.0; user-authorized | Global (user data) | Near real-time | V1 (optional OAuth) | V2: leverage Strava route images/notes where supported; deeper athlete context |  | All requests require authentication/scopes.
Route import (MapMyFitness) | MapMyFitness Route API | https://developer.mapmyfitness.com/docs/v71_Route/ | OAuth 2.0; developer integration | Global (user data) | Near real-time | V1 (optional) | V2: explore richer route metadata + social context if exposed |  | MapMyRide routes are accessible via MapMyFitness platform.
FIT parsing | Garmin FIT SDK | https://developer.garmin.com/fit/cookbook/ | SDK / local parsing | File-based | N/A | V1 | V2: expand FIT course support + device-specific fields |  | Use FIT SDK decode/encode guidance.
OSM surfaces + POIs | OpenStreetMap via Overpass API | https://wiki.openstreetmap.org/wiki/Overpass_API | Public query endpoints | Global | As-updated by OSM community | V1 (core) | V2: caching + heuristics; add paid places for reliable hours if needed |  | Surface/access tags vary in completeness.
Weather (US) | NWS API (api.weather.gov) | https://www.weather.gov/documentation/services-web-api | Open data; free; rate-limited | US | Forecast updates per NWS | V1 (core US) | V2: time-of-day ride planning + finer sampling | Open-Meteo (global dev): https://open-meteo.com/en/docs | NWS states open data and no fees; rate limits exist.
Weather (global dev) | Open-Meteo Forecast API | https://open-meteo.com/en/docs | No key; free for non-commercial; paid/self-host for commercial | Global | Model-dependent | V1 (fallback for non-US in dev) | V2: confirm commercial licensing (paid or self-host) OR swap provider |  | Treat as dev fallback until licensing aligns with business.
Weather alerts (US) | NWS Alerts API | https://www.weather.gov/documentation/services-web-alerts | Open data; free; rate-limited | US | Near real-time alerts | V1 (US) | V2: filter alerts by user start time + ETA |  | Attach alerts to nearest segments.
Public lands (US) | PAD-US (USGS) | https://data.usgs.gov/datacatalog/data/USGS%3A652ef930d34edd15305a9b03 | Downloads + web services | US | Periodic updates | V1 (core US) | V2: add access rules per land manager; improve state/local completeness where needed | Esri USA Federal Lands FeatureServer: https://services.arcgis.com/P3ePLMYs2RVChkJx/arcgis/rest/services/USA_Federal_Lands/FeatureServer | PAD-US includes all federal and most state/local lands.
State trust lands (US) | State-specific ArcGIS REST services (examples) | https://server.azgeo.az.gov/arcgis/rest/services/azland/State_Trust_Parcels/FeatureServer | Public ArcGIS REST (varies) | Selected states | Varies | V1 (best-effort only) | V2: build adapter registry per state; normalize schemas + caching | Utah SITLA: https://services9.arcgis.com/7i9gy0fV6OPIVl84/arcgis/rest/services/SITLAStateLandTrust/FeatureServer | State trust is fragmented; treat as best-effort.
Cell coverage (US) | FCC National Broadband Map | https://broadbandmap.fcc.gov/ | Public datasets/downloads | US | Periodic releases | V1 (US confidence layer) | V2: global coverage via OpenCelliD/crowdsourced + user-selected carrier | OpenCelliD: https://www.opencellid.org/ ¦ API wiki: https://wiki.opencellid.org/wiki/API | Coverage != guaranteed on-device service.
Trail conditions | Trailforks API (approval required) | https://www.trailforks.com/about/api/ | Request access; not guaranteed | Global-ish | User/association reports (dated) | V1 (only if approved) | V2: deeper integration + caching; add other trail sources | Trailforks mentions RSS/widgets on API page | Always show report date + attribution.
Route imagery (V1) | Mapillary API | https://www.mapillary.com/developer/api-documentation | Official API docs | Global (coverage varies) | As uploaded | V1 (optional) | V2: prefer Strava route/segment imagery where supported; keep Mapillary fallback | Strava (future): https://developers.strava.com/docs/reference/ | Documented: V2 aims for Strava-native imagery when available.
Private property borders | Defer (parcel data typically commercial) | https://geodata.colorado.gov/datasets/regrid%3A%3Aregrid-usa-nationwide-parcel-boundaries/about | Commercial/partner ecosystems | US | Varies | V1 (out of scope) | V2: add parcel layer as premium/region-specific; validate licensing | OSM access tags: https://wiki.openstreetmap.org/wiki/Key:access | Don't promise parcel-accurate borders in V1.
iOverlander / Roadtrippers | Defer unless partnership confirmed | https://roadtrippers.com/autopilot/ ¦ https://play.google.com/store/apps/details?id=com.ioverlander.ioverlander | No confirmed public API found in v1 research | Global | Varies | V1 (out) | V2: explore partnerships/licensed datasets |  | Track as V2 research items.

## Outputs_Spec
Output | Contents | Format | Release
Interactive map | Route polyline + toggleable overlays (surface, weather risk, water/resupply, public lands, coverage confidence, conditions, imagery points) | Web map with layers + side panel | V1
Route dossier | KPIs + supply gaps + alerts + land manager crossings + top risks + POI tables | Report panel + exportable JSON | V1
Plain-language plan | Planning narrative: resupply gaps, weather windows, bailouts, dead zones, latest trail reports | Markdown/text block | V1
Export bundle | Route JSON + enrichment JSON + source links | Download zip (optional) | V1
Enhanced imagery | Prefer Strava imagery/notes and richer route media where supported; fallback Mapillary | In-map photo cards | V2

## Risks_Assumptions
Risk / Assumption | Impact | Mitigation | Release
OSM tag completeness varies | Surface/hours/access may be missing in rural areas | Use confidence scoring + explicit 'unknown'; allow user feedback later | V1
Cell coverage data isn't real-time | May over/underestimate service | Label as 'coverage confidence'; enable carrier selection in V2 | V1
Trailforks API access not guaranteed | Conditions feature may be unavailable | Ship behind feature flag; add other sources later | V1
Municipal closures fragmented | Hard to cover globally | Plugin-based connectors; start with a few target regions | V2
Weather licensing varies | Global provider may require paid plan for commercial | Use NWS for US; treat Open-Meteo as dev fallback; decide licensing before launch | V1